## Product Backlog
MoSCoW ID | Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | Complexity | Risk/ Impact(L-Low, M- Medium, H-High) | Type | Comments
1 | 1 |  | M | Us: 101 | User Registration | Very Simple | L | Functional
2 | 2 |  | M | Us: 102 | User Login | Complex | M | Functional
3 | 3 |  | M | Us: 103 | User can schedule Appointment for Learning License | Simple | L | Functional
4 | 4 |  | M | Us: 104 | User can schedule Appointment for Driving License | Simple | L | Functional
5 | 5 |  | M | Us: 105 | User must fill the application form for Learning License/ Drivign License | Simple | M | Functional
6 | 6 |  | M | Us: 106 | User should be able to upload necessary documents | Average | M | Functional
7 | 7 |  | M | Us: 107 | User pays the Fees | Average | H | Functional
8 | 8 |  | S | Us: 108 | Verify Pay Status | Average | M | Functional
9 | 9 |  | S | Us: 109 | Generate Reciept | Simple | L | Functional
10 | 10 |  | M | Us: 110 | Book Slot for Learner License/ Driving License Test | Simple | L | Functional
11 | 11 |  | M | Us: 111 | Authenticate User Credentials While Login | Average | M | Functional
12 | 12 |  | S | Us: 112 | User should upload their photo for Driving License | Average | L | Functional
13 | 13 |  | S | Us: 113 | User should have a Unique Identification Number | Simple | L | Functional
14 | 14 |  | S | Us: 114 | User should be able change credentials | Simple | M | Functional
15 | 15 |  | M | Us: 115 | User LogOut | Very Simple | L | Functional
16 | 16 |  | M | Us: 116 | User can cancel appointment | Average | L | Functional
17 | 17 |  | S | Us: 117 | User should be able to attend exam | Average | H | Functional
18 | 18 |  | M | Us: 118 | User should be able to view Exam Results | Simple | L | Functional
19 | 19 |  | M | Us: 119 | RTO Login | Complex | M | Functional
20 | 20 |  | S | Us: 120 | RTO can Manage User (View/ Update/ Delete) | Average | L | Functional
21 | 21 |  | S | Us: 121 | RTO can Manage Licenses (Issue/ Renewal) | Complex | H | Functional
22 | 22 |  | S | Us: 122 | RTO can Manage Exam and Results | Average | M | Functional
23 | 23 |  | M | Us: 123 | RTO LogOut | Very Simple | L | Functional
25 | 25 |  | M | Us: 125 | RTO can Manage Applications (Pending/ Approved/ Rejected) | Average | L | Functional
26 | 26 |  | S | Us: 126 | RTO can Create and Manage Challan | Simple | L | Functional

## Sprint Backlog
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment
P:01 | US: 101 | 1 | POJO class for User | Shubham Paul | 07-21-2021 15:45 | 07-21-2021 17:00 | NIL | DONE
P:02 | US: 119 | 1 | POJO class for RTO Office | Riddhi Das | 07-21-2021 15:45 | 07-21-2021 17:00 | NIL | DONE
P:03 | US: 119 | 1 | POJO class for RTO Officer | Riddhi Das | 07-21-2021 15:45 | 07-21-2021 17:00 | NIL | DONE
P:04 | US: 105 | 1 | POJO class for Application | Shruti Masanta | 07-21-2021 15:45 | 07-21-2021 17:00 | NIL | DONE
P:05 | US: 103 | 1 | POJO class for Appointment | Shreya Sinha Roy | 07-21-2021 15:45 | 07-21-2021 17:00 | NIL | DONE
P:06 | US: 126 | 1 | POJO class for Challan | Rajarshi Bhattacharya | 07-21-2021 15:45 | 07-21-2021 17:00 | NIL | DONE
P:07 | US: 101 | 1 | POJO class for Address | Shruti Masanta | 07-21-2021 15:45 | 07-21-2021 17:00 | NIL | DONE
P:08 | US: 124 | 1 | POJO class for Driving License | Rajarshi Bhattacharya | 07-21-2021 15:45 | 07-21-2021 17:00 | NIL | DONE
P:09 | US: 105 | 1 | POJO class for Documents | Shreya Sinha Roy | 07-21-2021 15:45 | 07-21-2021 17:00 | NIL | DONE
P:10 | US: 105 | 1 | POJO class for Applicant | Shubham Paul | 07-21-2021 15:45 | 07-21-2021 17:00 | NIL | DONE
P:11 | US: 105 | 1 | Create ENUM for Application Type | Shubham Paul | 07-21-2021 15:45 | 07-21-2021 17:00 | NIL | DONE
P:12 | US: 105 | 1 | Create ENUM for Application Status | Riddhi Das | 07-21-2021 15:45 | 07-21-2021 17:00 | NIL | DONE
P:13 | US: 101 | 1 | Create ENUM for Gender | Rajarshi Bhattacharya | 07-21-2021 15:45 | 07-21-2021 17:00 | NIL | DONE
Make Database and apply annotation and all required validation in POJO class of User
Make Database and apply annotation and all required validation in POJO class of RTO Office
Make Database and apply annotation and all required validation in POJO class of Application
Make Database and apply annotation and all required validation in POJO class of Appointment
Make Database and apply annotation and all required validation in POJO class of Challan
Dao Implementation
Service Implementation
Controller methods
Dao Implementation
Service Implementation
Controller methods
Dao Implementation
Service Implementation
Controller methods
Dao Implementation
Service Implementation
Controller methods
Dao Implementation
Service Implementation
Controller methods
RTO Office Service Class
Application Service Class
Appointment Service Class
Challan Service Class
User Service Class
make front end for the guest user
make front end to welcome customer
make front end for the RTO Officer
make front end for submitting application
make front end for scheduling appointment